## PROJECT_DATA
Feature Name | Category | Status | Frontend UI % | Backend API % | Data Models % | Overall Completion % | Priority | Estimated Hours | Notes
Authentication System | Core | Complete | 100 | 100 | 100 | 95 | Critical | 0.5 | Has 1 critical bug in line 383 - email parameter
Dashboard | Core | Complete | 100 | 100 | 100 | 95 | High | 2 | Minor improvements needed
Send SMS | Core | Complete | 100 | 100 | 100 | 90 | High | 5 | Core functionality working
Message History | Core | Complete | 100 | 100 | 100 | 85 | High | 3 | API integration complete
Templates Management | Core | Complete | 100 | 100 | 100 | 90 | High | 4 | Fixed data mapping issues
Groups Management | Core | Complete | 100 | 100 | 100 | 85 | High | 4 | API integration complete
Contacts Management | Core | Complete | 100 | 100 | 100 | 80 | High | 5 | Role-based filtering working
User Management | Core | Complete | 100 | 100 | 100 | 85 | Medium | 3 | Admin-only access implemented
Template Approvals | Admin | Partial | 100 | 0 | 100 | 40 | High | 20 | UI complete, needs backend APIs
Sender ID Management | Admin | Partial | 100 | 0 | 50 | 35 | High | 20 | No backend endpoints, DLT workflow needed
Reports & Analytics | Admin | Partial | 100 | 20 | 100 | 30 | Medium | 30 | Mock data in charts
Settings Management | Admin | Partial | 100 | 0 | 50 | 25 | Medium | 15 | No persistence, needs API endpoints
User Registration | Admin | Partial | 50 | 0 | 100 | 10 | Low | 20 | Form exists but disabled, needs backend
Activity/Audit Log | Admin | Not Started | 20 | 0 | 0 | 0 | Low | 25 | Basic stub only
API Endpoint | Method | Status | Implementation Notes | Priority
/api/token/ | POST | Complete | JWT token generation | Core
/api/templates/ | GET | Complete | List all templates | Core
/api/templates/ | POST | Complete | Create template | Core
/api/groups/ | GET | Complete | List groups | Core
/api/groups/ | POST | Complete | Create group | Core
/api/contacts/ | GET | Complete | List contacts | Core
/api/messages/ | GET | Complete | Message history | Core
/api/send/ | POST | Complete | Send SMS | Core
/api/campaigns/ | GET | Complete | List campaigns | Core
/api/campaigns/ | POST | Complete | Create campaign | Core
/api/users/ | GET | Complete | List users (admin) | Core
/api/dashboard/stats/ | GET | Complete | Dashboard metrics | Core
/api/templates/<id>/approve/ | POST | Not Implemented | Approve template | High
/api/templates/<id>/reject/ | POST | Not Implemented | Reject template | High
/api/templates/bulk-approve/ | POST | Not Implemented | Bulk approve | High
/api/sender-ids/ | GET | Not Implemented | List sender IDs | High
/api/sender-ids/ | POST | Not Implemented | Create sender ID | High
/api/sender-ids/<id>/ | DELETE | Not Implemented | Delete sender ID | High
/api/reports/summary/ | GET | Partial | Report data | Medium
/api/reports/export/ | POST | Not Implemented | Export CSV/PDF | Medium
/api/settings/profile/ | GET | Not Implemented | Get settings | Medium
/api/settings/profile/ | PUT | Not Implemented | Update settings | Medium
/api/settings/change-password/ | POST | Not Implemented | Change password | Medium
Database Model | Fields Count | Relationships | Status | Notes
User | 11 | OneToMany (Templates Groups Messages) | Complete | Email-based auth with roles
Template | 10 | ForeignKey (User) | Complete | SMS templates with variables
Group | 5 | ForeignKey (User) ManyToMany (Contacts) | Complete | Contact groupings
StudentContact | 8 | ManyToMany (Groups) | Complete | Contact records
SenderID | 7 | ForeignKey (User) | Complete | Approved sender IDs
Campaign | 8 | ForeignKey (User) | Complete | SMS campaigns
SMSMessage | 12 | ForeignKey (User Campaign) | Complete | Message records
SMSRecipient | 10 | ForeignKey (SMSMessage) | Complete | Individual recipient logs
APICredentials | 6 | OneToOne (User) | Complete | API keys per user
SMSUsageStats | 6 | OneToOne (User) | Complete | Credit tracking
Security Item | Status | Risk Level | Action Required
CSRF Protection | Enabled | Low | Maintain
Password Hashing | PBKDF2 | Low | Maintain
Session Cookies | HttpOnly | Low | Maintain
Role-Based Access | Implemented | Low | Maintain
SQL Injection Protection | ORM | Low | Maintain
XSS Protection | Template Escaping | Low | Maintain
DEBUG Mode | Enabled | High | Disable in production
SECRET_KEY Exposure | Exposed in .env | High | Use environment variables
Rate Limiting | Not Implemented | Medium | Implement django-ratelimit
Password Complexity | None | Medium | Add validation rules
Email Verification | Not Implemented | Medium | Add to registration
2FA | Not Implemented | Low | Consider for admin accounts
Task | Priority | Status | Estimated Hours | Dependencies | Deliverable
Fix Authentication Bug | Critical | Pending | 0.5 | None | Working login
End-to-End Testing | Critical | Pending | 2 | Bug fix | Test report
Template Approvals Backend | High | Pending | 20 | None | API endpoints + email notifications
Sender ID Management | High | Pending | 20 | None | CRUD APIs + DLT workflow
Settings Persistence | High | Pending | 15 | None | Settings API + password change
Reports Implementation | Medium | Pending | 30 | None | Chart APIs + export functionality
User Registration | Medium | Pending | 20 | None | Registration endpoint + verification
Activity Log System | Low | Pending | 25 | None | Activity model + middleware + API
Advanced Features | Low | Future | 120 | All above | Scheduled SMS + webhooks + multi-language
Performance Optimization | Low | Future | 80 | All above | Caching + query optimization + Celery
Security Hardening | Low | Future | 40 | All above | Audit + rate limiting + validation
Unit Tests | Medium | Pending | 100 | None | 80%+ test coverage
API Documentation | Medium | Pending | 10 | None | Complete API docs
Deployment Guide | Medium | Pending | 8 | Security | Production deployment steps
User Manual | Low | Pending | 15 | All features | End-user documentation
Technology | Version | Purpose | Status
Django | 4.2.7 | Backend Framework | Installed
Django REST Framework | Latest | API Development | Installed
MySQL | Latest | Database | Configured
JWT | simplejwt | API Authentication | Configured
Bootstrap | 5.3.3 | Frontend UI | Integrated
Font Awesome | 6.0.0 | Icons | Integrated
Chart.js | Latest | Reports Visualization | Partially Integrated
Python | 3.x | Programming Language | Active
PowerShell | 5.1 | Shell Environment | Active
Git | Latest | Version Control | Active
Metric | Value | Category | Notes
Total Features | 14 | Project Scope
Completed Features | 8 | Progress | 57% of total
Partial Features | 5 | Progress | 36% of total
Not Started Features | 1 | Progress | 7% of total
Overall Completion | 65% | Progress
Core Features Completion | 87% | Progress | Functional MVP
Admin Features Completion | 30% | Progress | Needs backend work
Total Code Lines (Backend) | ~1000 | Code Quality | Views + Models + Utils
Total HTML Templates | 14 | Frontend | All pages designed
API Endpoints Implemented | 12 | Backend
API Endpoints Needed | 23 | Backend | Total required
Critical Issues | 1 | Quality | Authentication bug
Medium Issues | 3 | Quality | Mock data + missing APIs
Estimated Hours Remaining | 140 | Planning | Maximum estimate
Estimated Weeks Remaining | 3.5 | Planning | Full-time development
Monthly Maintenance Hours | 40 | Operations | Bug fixes + enhancements
Phase | Status | Completion % | Features Included | Timeline
Phase 1: Core Features | Complete | 100% | Auth Dashboard Send-SMS History Templates Groups Contacts Users | Current
Phase 2: Admin Features | In Progress | 30% | Approvals Sender-IDs Reports Settings Registration Activity-Log | 1-2 months
Phase 3: Production Ready | Future | 0% | Testing Security Performance Documentation Deployment | 2-3 months